## Activity Tracker
Project
Project time tracker for knowing time used on project | [8 empty] | Total minutes | 2620 | Minutes
Planning | 0
|  | Hours | [6 empty] | Total hours | 43.6667 | Hours
| 0 | Minutes | Date | Subject | Start Time | Duration | Minutes | Note
|  |  | 2018-02-19 | Designing | 13:20 | 5:00 | 300 | Created a test player character, player animations, sword and floor. Forgot to make elbows and knees on the character models
Unity | 31.1667 |  | 2018-02-21 | Unity | 11:40 | 0:40 | 40 | Messed around in unity and inserted my test character and set up folder/unity
|  | Hours | 2018-02-21 | Unity | 19:50 | 4:40 | 280 | Continued on the test character in unity. Made the character able to jump, walk and gave it a sword.
| 1870 | Minutes | 2018-02-22 | Unity | 14:00 | 1:20 | 80 | Made the start area game scene a basic cube for testing and script for basic movement
|  |  | 2018-02-22 | Unity | 22:55 | 0:40 | 40 | made the camera third persion and made the player walk toward the camera direction and the player turn with the camera
Designing | 12.5 |  | 2018-02-24 | Designing | 12:40 | 2:10 | 130 | Started to create the player, a lot of trial and error
|  | Hours | 2018-02-24 | Designing | 17:40 | 5:20 | 320 | Started on the model for the character that will most likely be the player
| 750 | Minutes | 2018-02-25 | Unity | 13:00 | 2:20 | 140 | Made an enemy slime that is able to move, locate the player and attack the player. Also gave the player health
|  |  | 2018-02-27 | Unity | 21:00 | 2:00 | 120 | Messed around with the controllers and tested with some prefab characters from Unity to understand how they work
Testing | 0 |  | 2018-03-01 | Unity | 18:30 | 3:30 | 210 | Worked on the player movement
|  | Hours | 2018-03-02 | Unity | 18:20 | 2:00 | 120 | I tried to make the movement work, END ME
| 0 | Minutes | 2018-03-04 | Unity | 15:00 | 1:45 | 105 | Finnaly got the basic movements to work and can move in the direction of the camera
|  |  | 2018-03-05 | Unity | 22:20 | 0:40 | 40 | Fixed up some of the movement code so it is more cohesive
|  |  | 2018-03-06 | Unity | 22:00 | 1:00 | 60 | Made the player face the direction it was moving, started woking on the jump and made the code better
|  |  | 2018-03-07 | Unity | 12:40 | 2:05 | 125 | Tried out different ways of making the character jump, made the character look in the direction it is walking, if the character is not walking it looks in the direction of the camera
|  |  | 2018-03-09 | Unity | 18:15 | 0:40 | 40 | Made the character only able to jump when grounded
|  |  | 2018-03-14 | Unity | 22:00 | 1:00 | 60 | Started making the input manager, sat up forward, backward, left, right and jump
|  |  | 2018-03-15 | Unity | 12:00 | 3:30 | 210 | Made the pauseMenu and made it so you can change the inputs on the keys, although they are not being used.
|  |  | 2018-03-17 | Unity | 14:00 | 3:20 | 200 | Added dash, crouch, interact, inventory and attack to the game manager. Made the custom inputs br what controls the character instead of unitys (except for W, A, S, D and attack)

## Activity List (hidden)
Activity List
The list below is tied to the custom activities and populates the drop down list on the Activity Log. This sheet should remain hidden.
Activity | Unit
Planning | Hours
Unity | Hours
Designing | Hours
#REF! | #REF!
#REF! | #REF!