## Activity Tracker
Project
Project time tracker for knowing time used on project | [8 empty] | Total minutes | 7060 | Minutes
[9 empty] | Total hours | 117.6667 | Hours
|  |  | Date | Subject | Start Time | Duration | Minutes | Note
|  |  | 2018-02-19 | Designing | 13:20 | 5:00 | 300 | Created a test player character, player animations, sword and floor. Forgot to make elbows and knees on the character models
Unity | 105.1667 |  | 2018-02-21 | Unity | 11:40 | 0:40 | 40 | Messed around in unity and inserted my test character and set up folder/unity
|  | Hours | 2018-02-21 | Unity | 19:50 | 4:40 | 280 | Continued on the test character in unity. Made the character able to jump, walk and gave it a sword.
| 6310 | Minutes | 2018-02-22 | Unity | 14:00 | 1:20 | 80 | Made the start area game scene a basic cube for testing and script for basic movement
|  |  | 2018-02-22 | Unity | 22:55 | 0:40 | 40 | made the camera third persion and made the player walk toward the camera direction and the player turn with the camera
Designing | 12.5 |  | 2018-02-24 | Designing | 12:40 | 2:10 | 130 | Started to create the player, a lot of trial and error
|  | Hours | 2018-02-24 | Designing | 17:40 | 5:20 | 320 | Started on the model for the character that will most likely be the player
| 750 | Minutes | 2018-02-25 | Unity | 13:00 | 2:20 | 140 | Made an enemy slime that is able to move, locate the player and attack the player. Also gave the player health
|  |  | 2018-02-27 | Unity | 21:00 | 2:00 | 120 | Messed around with the controllers and tested with some prefab characters from Unity to understand how they work
|  |  | 2018-03-01 | Unity | 18:30 | 3:30 | 210 | Worked on the player movement
|  |  | 2018-03-02 | Unity | 18:20 | 2:00 | 120 | I tried to make the movement work, END ME
|  |  | 2018-03-04 | Unity | 15:00 | 1:45 | 105 | Finnaly got the basic movements to work and can move in the direction of the camera
|  |  | 2018-03-05 | Unity | 22:20 | 0:40 | 40 | Fixed up some of the movement code so it is more cohesive
|  |  | 2018-03-06 | Unity | 22:00 | 1:00 | 60 | Made the player face the direction it was moving, started woking on the jump and made the code better
|  |  | 2018-03-07 | Unity | 12:40 | 2:05 | 125 | Tried out different ways of making the character jump, made the character look in the direction it is walking, if the character is not walking it looks in the direction of the camera
|  |  | 2018-03-09 | Unity | 18:15 | 0:40 | 40 | Made the character only able to jump when grounded
|  |  | 2018-03-14 | Unity | 22:00 | 1:00 | 60 | Started making the input manager, sat up forward, backward, left, right and jump
|  |  | 2018-03-15 | Unity | 12:00 | 3:30 | 210 | Made the pauseMenu and made it so you can change the inputs on the keys, although they are not being used.
|  |  | 2018-03-17 | Unity | 14:00 | 3:20 | 200 | Added dash, crouch, interact, inventory and attack to the game manager. Made the custom inputs br what controls the character instead of unitys (except for W, A, S, D and attack)
|  |  | 2018-03-24 | Unity | 10:15 | 2:00 | 120 | Started on the optionsmenu and added back buttons on inputmeny and optionsmenu, and polished up code/UI
|  |  | 2018-03-25 | Unity | 14:15 | 2:30 | 150 | Worked on the playermovement, trying to make the jump, dash and crouch to work as intended.
|  |  | 2018-04-01 | Unity | 10:10 | 3:00 | 180 | Created the UI for the default screen and worked on getting the interactions to work
|  |  | 2018-04-05 | Unity | 12:10 | 2:00 | 120 | Worked on the inventory system, managed to create 2 inventory systems, one for the player and one for the players proximity.
|  |  | 2018-04-07 | Unity | 11:00 | 3:00 | 180 | Continued on making the interactions. Started on making the different panels for dialogue, trading and quest log
|  |  | 2018-04-08 | Unity | 9:30 | 2:00 | 120 | Finnished creating the oprions menu, added apply button, fullscreen toggle, resolution, texture quality, anti aliasing, vsync and audio volume
|  |  | 2018-04-10 | Unity | 11:30 | 2:30 | 150 | Created the dialogue for talking to an NPC
|  |  | 2018-04-14 | Unity | 14:00 | 1:10 | 70 | Created scripts for character stats and started on the equip weapon.
|  |  | 2018-04-19 | Unity | 9:40 | 2:20 | 140 | Integrated the animations for the temporarly player so i coudl get the logic and code down
|  |  | 2018-04-20 | Unity | 10:10 | 2:15 | 135 | Started on the equpWeapon and inventory controller
|  |  | 2018-04-27 | Unity | 15:10 | 1:30 | 90 | Started on the weaponAttack
|  |  | 2018-04-29 | Unity | 11:30 | 1:20 | 80 | Got done with the basicAttack of the character. Can now swing a weapon and damage an enemy, still only have a stand in model
|  |  | 2018-05-02 | Unity | 10:30 | 1:15 | 75 | Hooked up the healthSlider to code so it changes based on the players health and the numbers show the players healt. Started working on item consumables.
|  |  | 2018-05-03 | Unity | 10:10 | 2:30 | 150 | Refactored some of the code so the gameobjects is added in the code automatically if they are null instead of adding them all manually. Created consumables and consumablescontroller
|  |  | 2018-05-05 | Unity | 10:00 | 4:45 | 285 | Created the item database, created the ui for my inventory and made the ui work with the item database.
|  |  | 2018-05-06 | Unity | 10:05 | 1:50 | 110 | Added item stats to the inventory system so they are properly displayed, added icons so they are properly displayed and tried to make IPickUp work on items. And made it so the inventory opens and closes as it should and pauses the game while open.
|  |  | 2018-05-06 | Unity | 15:05 | 0:45 | 45 | Refactored the characterstats
|  |  | 2018-05-07 | Unity | 11:15 | 1:40 | 100 | Added a slime that the player can kill and that can kill the player.
|  |  | 2018-05-07 | Unity | 14:15 | 1:15 | 75 | Made the weapons that were equipped go back in the inventory when another weapon was equipped and refactored/added damage and crit
|  |  | 2018-05-08 | Unity | 13:20 | 3:05 | 185 | Refactored the playerhealth and slime so the slime uses attackDamage, armour and attackSpeed, the player uses armour and attackDamage. Added Death animation. Added characterStats and equipped weaponn UI on the inventory UI
|  |  | 2018-05-09 | Unity | 11:00 | 3:50 | 230 | Created events for level, health and stats, made the UI update the inventory stats for the player and the equipped weapon. The ui updates the health, experience and level. Added level to the player.
|  |  | 2018-05-10 | Unity | 8:45 | 2:35 | 155 | created item pickup, so the player is able to pick up items that monsters drop. Created monster spawner
|  |  | 2018-05-12 | Unity | 10:40 | 2:30 | 150 | Created questing
|  |  | 2018-05-13 | Unity | 10:00 | 4:00 | 240 | Created the starting are with an NPC to introduce the player to the game. Created portals.
|  |  | 2018-05-15 | Unity | 9:00 | 5:00 | 300 | Created passages that is used to transport the player between areas that are next to eachother. Started on setting the town together
|  |  | 2018-05-16 | Unity | 8:35 | 2:00 | 120 | Worked on making enemies have animations and the city.
|  |  | 2018-05-16 | Unity | 13:35 | 1:05 | 65 | Worked on the animator for monsters/enemies and refactored the way the loot works
|  |  | 2018-05-17 | Unity | 9:20 | 4:00 | 240 | Created weapons and potions. Worked on the town and start are. Added lights. Refactored the passages to work better.
|  |  | 2018-05-18 | Unity | 9:00 | 3:45 | 225 | Worked on the story of the game and started to add NPC's with quests that are tied to the story.
|  |  | 2018-05-19 | Unity | 8:30 | 2:35 | 155 | Started to work on the collect quest so it count properly on the items collected and made the quest giver remove th item from the players list(not UI)

## Activity List (hidden)
Activity List
The list below is tied to the custom activities and populates the drop down list on the Activity Log. This sheet should remain hidden.
Activity | Unit
0
Unity | Hours
Designing | Hours
#REF! | #REF!
#REF! | #REF!